## Slide 1
Start Mon 23/07/18
Finish Fri 12/10/18
23 Jul '18
30 Jul '18
6 Aug '18
13 Aug '18
20 Aug '18
27 Aug '18
3 Sep '18
10 Sep '18
17 Sep '18
24 Sep '18
1 Oct '18
8 Oct '18
Sprint 1
Mon 6/08/18 - Sun 26/08/18
Sprint 2
Mon 27/08/18 - Sun 16/09/18
Kick-Off
Mon 23/07/18 - Sun 5/08/18
Sprint 3
Mon 17/09/18 - Fri 12/10/18
M1 - Audit #1
6/08 - 10/08
M4 - Audit #2 27/08 - 31/08
M5 - Audit #3
8/10 - 12/10
User Testing 1 17/08 - 22/08
User Testing 2 5/09 - 10/09
Public User Testing
17/09 - 23/09
Testing 4
3/10 - 6/10
TechLauncher Showcase Thu 11/10/18
Project Poster Complete Fri 5/10/18
Client Meeting 1 Tue 31/07/18
Client Meeting 4 Tue 21/08/18
Client Meeting 2 Tue 7/08/18
Client Meeting 3 Tue 14/08/18
Client Meeting 5 Tue 28/08/18
Client Meeting 6 Tue 4/09/18
Client Meeting 7 Tue 11/09/18
Client Meeting 8 Tue 18/09/18
Client Meeting 9 Tue 25/09/18
Client Meeting 10 Tue 2/10/18
M2 - Initial Deployment
M3 - Technical Debt Removed Fri 17/08/18
Mid-Sprint Review 3 Fri 28/09/18
Mid-Sprint Review 2 Fri 7/09/18
Mid-Sprint Review 1 Sun 19/08/18
Team Meeting 1 Mon 30/07/18
Team Meeting 2 Mon 6/08/18
Team Meeting 3 Mon 13/08/18
Team Meeting 4 Mon 20/08/18
Team Meeting and Retrospective 5 Mon 27/08/18
Team Meeting 6 Mon 3/09/18
Team Meeting 7 Mon 10/09/18
Team Meeting and Retrospective 8 Mon 17/09/18
Team Meeting 9 Mon 24/09/18
Team Meeting 10 Mon 1/10/18
Team Meeting 11 Mon 8/10/18